## Rates
Project summary
Approved PJD
Project Lead
| Project Manager | Tasha Rockliff
| ProgramArea Manager | Insert name
| Links to task specifications | Insert link(s) | [12 empty] | =((D7*'Project Overview'!'Project Overview'!42:42D42)+(E7*'Project Overview'!D23)+(F7*'Project Overview'!D24))*1.4
Total person resource hours
Total capital spend
|  | Cost.cat | FY25/26 | FY26/27 | FY27/28 | FY28/29 | Overhead Rate | 1.4
|  | UKA1 | 17.32 | 18.0128 | 18.7333 | 19.4826
|  | UKA2 | 38.85 | 40.404 | 42.0202 | 43.701
|  | UKL1 | 26.43 | 27.4872 | 28.5867 | 29.7302
|  | UKL2 | 26.43 | 27.4872 | 28.5867 | 29.7302
|  | UKL3 | 30.85 | 32.084 | 33.3674 | 34.7021
|  | UKL4 | 38.75 | 40.3 | 41.912 | 43.5885
|  | UKL5 | 48.03 | 49.9512 | 51.9492 | 54.0272
|  | UKL6 | 62.14 | 64.6256 | 67.2106 | 69.899
|  | UKL7 | 74.05 | 77.012 | 80.0925 | 83.2962 |  | Estimate F and H as halfway between grades
|  | UKL8 | 104.9 | 109.096 | 113.4598 | 117.9982 |  | FY25/26 | FY26/27 | FY27/28 | FY28/29 |  | 26/27
22 | UKM3 | UKM3 | 35.29 | 36.7016 | 38.1697 | 39.6965 | UKAXF | 47.205 | 49.0932 | 51.0569 | 53.0992 | UKAXF | I22
23 | UKM4 | UKM4 | 40.4 | 42.016 | 43.6966 | 45.4445 | UKAXH | 60.785 | 63.2164 | 65.7451 | 68.3749 | UKAXH | I23
24 | UKM5 | UKM5 | 54.01 | 56.1704 | 58.4172 | 60.7539 | [7 empty] | 0
25 | UKM6 | UKM6 | 67.56 | 70.2624 | 73.0729 | 75.9958 | Year In Industry |  | 15.1175 | 15.7222 | 16.351
|  | UKM7 | 88.78 | 92.3312 | 96.0244 | 99.8654 |  |  | Year in Industry = 23,810
|  | UKMS | 52.67 | 54.7768 | 56.9679 | 59.2466
|  | UKS3 | 46.7 | 48.568 | 50.5107 | 52.5311
|  | UKS4 | 54 | 56.16 | 58.4064 | 60.7427
|  | UKT1 | 23.14 | 24.0656 | 25.0282 | 26.0294
|  | RU01 | 11.5 | 11.96 | 12.4384 | 12.9359
|  | RU02 | 14.75 | 15.34 | 15.9536 | 16.5917
|  | RU03 | 16.5 | 17.16 | 17.8464 | 18.5603
|  | RU04 | 19.25 | 20.02 | 20.8208 | 21.6536
|  | RU05 | 21.5 | 22.36 | 23.2544 | 24.1846
|  | RU06 | 23.75 | 24.7 | 25.688 | 26.7155
|  | RU07 | 26.5 | 27.56 | 28.6624 | 29.8089
|  | RU08 | 29 | 30.16 | 31.3664 | 32.6211
|  | RU09 | 31.25 | 32.5 | 33.8 | 35.152
|  | RU10 | 33.75 | 35.1 | 36.504 | 37.9642
|  | RU11 | 36.5 | 37.96 | 39.4784 | 41.0575
|  | RU12 | 38.5 | 40.04 | 41.6416 | 43.3073
|  | RU13 | 41.5 | 43.16 | 44.8864 | 46.6819
|  | RU14 | 44.25 | 46.02 | 47.8608 | 49.7752
|  | RU15 | 48 | 49.92 | 51.9168 | 53.9935
|  | RU16 | 53.25 | 55.38 | 57.5952 | 59.899
|  | RU17 | 58.5 | 60.84 | 63.2736 | 65.8045
|  | RU18 | 64.5 | 67.08 | 69.7632 | 72.5537
|  | RU19 | 70 | 72.8 | 75.712 | 78.7405
|  | RU20 | 75.85 | 78.884 | 82.0394 | 85.3209
|  | RU23 | 81.7 | 84.968 | 88.3667 | 91.9014
|  | RU24 | 87.55 | 91.052 | 94.6941 | 98.4818
|  | RU25 | 90 | 93.6 | 97.344 | 101.2378
|  | RU26 | 95 | 98.8 | 102.752 | 106.8621
|  | RU27 | 100 | 104 | 108.16 | 112.4864
|  | RU28 | 105 | 109.2 | 113.568 | 118.1107
|  | RU29 | 110 | 114.4 | 118.976 | 123.735
|  | RU30 | 115 | 119.6 | 124.384 | 129.3594
|  | RU31 | 120 | 124.8 | 129.792 | 134.9837
|  | RU32 | 125 | 130 | 135.2 | 140.608
|  | UNI2 | 56.7 | 58.968 | 61.3267 | 63.7798
|  | IND1 | 110 | 114.4 | 118.976 | 123.735
|  | IND2 | 72 | 74.88 | 77.8752 | 80.9902
|  | IND3 | 55 | 57.2 | 59.488 | 61.8675
|  | IND4 | 65 | 67.6 | 70.304 | 73.1162
|  | IND5 | 82 | 85.28 | 88.6912 | 92.2388
|  | IND6 | 69 | 71.76 | 74.6304 | 77.6156
|  | IND7 | 38 | 39.52 | 41.1008 | 42.7448
|  | IND8 | 60 | 62.4 | 64.896 | 67.4918
|  | IND9 | 90 | 93.6 | 97.344 | 101.2378
|  | IND10 | 120 | 124.8 | 129.792 | 134.9837
|  | IND11 | 100 | 104 | 108.16 | 112.4864
|  | IND12 | 50 | 52 | 54.08 | 56.2432
|  | IND13 | 65 | 67.6 | 70.304 | 73.1162
|  | IND14 | 70 | 72.8 | 75.712 | 78.7405
|  | IND15 | 55 | 57.2 | 59.488 | 61.8675
|  | IND16 | 105 | 109.2 | 113.568 | 118.1107
|  | IND17 | 95 | 98.8 | 102.752 | 106.8621
|  | IND18 | 46 | 47.84 | 49.7536 | 51.7437
|  | IND19 | 115 | 119.6 | 124.384 | 129.3594
|  | IND20 | 170 | 176.8 | 183.872 | 191.2269
|  | IND21 | 135 | 140.4 | 146.016 | 151.8566
|  | IND22 | 129 | 134.16 | 139.5264 | 145.1075
|  | IND23 | 87 | 90.48 | 94.0992 | 97.8632
|  | IND24 | 160 | 166.4 | 173.056 | 179.9782
|  | IND25 | 77 | 80.08 | 83.2832 | 86.6145
|  | IND26 | 125 | 130 | 135.2 | 140.608

## June 26 - UKAEA (hidden)
Project Dashboard- WON 13875-1000
Month | Forecasted Hours | [18 empty] | Forcasted Spend |  | Annual Budget |  | Actual Spend | Total Project Cost - Overview
| Lloyd Fletcher | Joel Hirst | Joel Hirst | Wiera Bielajewa | Christopher Dawson | Adel Tayeb | Nell Morris | Rory Spencer | Megan Sampson | Alexander Marsh | John Charlton | FC - Total | Rushavya Naidu | Lucas Pigott | Student 1 | Student 2 | Total PhD Cost | Travel | External Spend | UKAEA Resource Spend ONLY | UKAEA Forecast Spend | UKAEA Annual Budget | Variance from Budget | Actual Spend to date
Grade | UKAXI | UKAXE | UKAXG | UKAXE | UKAXE | UKM5 | UKL3 | UKM5 | UKM4 | UKM4 | UKM4 |  | PhD Student
FTE | 0.3 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 | 0.2 | 1 | 0
FY24/25 | 24 | 0 | 0 | 0 | 0 | 948 | 0 | 0 | 0 | 809 | 0 | 1781 |  |  |  |  | 0 | 627 | 215 | 0 | 0 | 0 |  | 95819.57 | Project Budget
FY25/26 | 1091 | 949 | 0 | 780 | 0 | 957 | 10 | 58 | 358 | 1393 | 251 | 5847 | 7778 | 8072 | 0 | 0 | 15850 | 4370 | 27014 | 0 | 0 | 300000 |  | 268870.79
FY26/27 | 472.5 | 0 | 0 | 0 | 0 | 1417.5 | 0 | 0 | 315 | 1575 | 0 | 3780 | 15685 | 16378 | 7924.5 | 7924.5 | 47912 | 18000 | 47911 | 112609.224 | 226432.224 | 381973.39 | 155541.166 | 30849.55 | 1255259.7
FY27/28 | 472.5 | 0 | 0 | 0 | 0 | 1417.5 | 0 | 0 | 315 | 1575 | 0 | 3780 | 15945.25 | 16854 | 16030.5 | 16030.5 | 64860.25 | 18000 | 64860 | 117113.593 | 264833.843 | 381973.39 | 117139.547
FY28/29 | 236.25 | 0 | 0 | 0 | 0 | 708.75 | 0 | 0 | 157.5 | 787.5 | 0 | 1890 | 8105.125 | 8674 | 16399.5 | 16399.5 | 49578.125 | 9000 | 33106 | 60899.0683 | 152583.1933 | 95493.35 | -57089.8433 |  | Forecast Cost at Completion
FAC | 2296.25 | 949 | 0 | 780 | 0 | 5448.75 | 10 | 58 | 1145.5 | 6139.5 | 251 | 17078 | 47513.375 | 49978 | 40354.5 | 40354.5 | 178200.375 | 49997 | 173106 | 290621.8853 | 643849.2603 | 1159440.13 |  | 395539.91 | 1008539.6203
Note on AD14: Rockliff, Tasha: Amend with each update

## UKAEA
Project Dashboard- WON 13875-1000
Month | Forecasted Hours | [22 empty] | Forcasted Spend |  | Annual Budget |  | Actual Spend | Total Project Cost - Overview
| Lloyd Fletcher | Joel Hirst | Joel Hirst | Wiera Bielajewa | Wiera Bielajewa | Adel Tayeb | Adel Tayeb | Rob Hamill | Graduates | Year in Industry | Nell Morris | Rory Spencer | Megan Sampson | Alexander Marsh | John Charlton | FC - Total | Rushavya Naidu | Lucas Pigott | Student 1 | Student 2 | Total PhD Cost | Travel | External Spend | UKAEA Resource Spend ONLY | UKAEA Forecast Spend | UKAEA Annual Budget | Variance from Budget | Actual Spend to date
Grade | UKAXI | UKAXE | UKAXG | UKAXE | UKAXF | UKM5 | UKAXH | UKAXF | UKL3 | - | UKL3 | UKM5 | UKM4 | UKM4 | UKM4 |  | PhD Student
FTE | 0.3 | 0 | 0 | 0 | 0 | 0.9 | 0.9 | 1 | 1 | 1 | 0 | 0 | 0.2 | 1 | 0
FY24/25 | 24 | 0 | 0 | 0 | 0 | 948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 809 | 0 | 1781 |  |  |  |  | 0 | 627 | 215 | 0 | 0 | 0 |  | 95819.57 | Project Budget
FY25/26 | 1091 | 949 | 0 | 780 | 780 | 957 | 0 | 0 | 0 | 0 | 10 | 58 | 358 | 1393 | 251 | 6627 | 7778 | 8072 | 0 | 0 | 15850 | 4370 | 27014 | 0 | 0 | 300000 |  | 268870.79
FY26/27 | 472.5 | 0 | 0 | 0 | 0 | 0 | 945 | 656.25 | 0 | 0 | 0 | 0 | 472.5 | 420 | 0 | 2966.25 | 15685 | 16378 | 7924.5 | 7924.5 | 47912 | 15000 | 0 | 227717.2443 | 290629.2443 | 381973.39 | 91344.1457 | 30849.55 | 1255259.7
FY27/28 | 472.5 | 0 | 0 | 0 | 0 | 0 | 1417.5 | 1575 | 0 | 0 | 0 | 0 | 157.5 | 0 | 0 | 3622.5 | 15945.25 | 16854 | 16030.5 | 16030.5 | 64860.25 | 15000 | 0 | 301024.4197 | 380884.6697 | 381973.39 | 1088.7203
FY28/29 | 196.875 | 0 | 0 | 0 | 0 | 0 | 590.625 | 656.25 | 0 | 0 | 0 | 0 | 65.625 | 0 | 0 | 1509.375 | 8105.125 | 8674 | 16399.5 | 16399.5 | 49578.125 | 7500 | 0 | 130443.9152 | 187522.0402 | 95493.35 | -92028.6902 |  | Forecast Cost at Completion
FAC | 2256.875 | 949 | 0 | 780 | 780 | 1905 | 2953.125 | 2887.5 | 0 | 0 | 10 | 58 | 1053.625 | 2622 | 251 | 16506.125 | 47513.375 | 49978 | 40354.5 | 40354.5 | 178200.375 | 42497 | 27229 | 659185.5792 | 859035.9542 | 1159440.13 |  | 395539.91 | 1223726.3142
[8 empty] | Starts Dec 2026 | [5 empty] | Resigns end July 2026 | [8 empty] | All external spend is on PhDs - no other external spend
Note on AH14: Rockliff, Tasha: Amend with each update

## June 26 - UKRI (hidden)
Project Dashboard- WON 12570-1022 - UKRI
Month | Forecasted Hours | [8 empty] | External Forecast |  |  |  |  | UKRI Cost - Overview
| Lloyd Fletcher | Joel Hirst | Joel Hirst | Wiera Bielajewa | Jonathan Horne-Jones | John Charlton | Graduate (TBC) | Christopher Dawson | FC Hours - Total | Travel | External Spend | UKRI Forecast Spend (80% +All expenses) | UKAEA Shortfall (20%) £401,349 Budget | Total Spend to date - UKRI ONLY
Grade | UKAXI | UKAXE | UKAXG | UKAXE |  |  | UKL3 | UKAXE
FY24/25 | 874 | 527 | 0 | 0 | 0 | 570 | 0 | 0 |  | 642 | 5232 | 0 | 0 | 116616.82 | Grant Contribution Budget
FY25/26 | 1091 | 949 | 0 | 780 | 7 | 251 | 0 | 1575 |  | 5048 | 17738 | 0 | 0 | 211853.97
FY26/27 | 945 | 0 | 1575 | 1102.5 | 0 | 0 | 787 | 120 | 4529.5 | 32492 | 32492 | 324242.7379 | 71705.037 | 43314 | 1605398
FY27/28 | 945 | 0 | 1575 | 1102.5 | 0 | 0 | 1575 | 0 | 5197.5 | 32492 | 32492 | 358188.9563 | 81625.1148
FY28/29 | 236.25 | 0 | 393.75 | 275.625 | 0 | 0 | 393.75 | 0 | 1299.375 | 29555 | 29555 | 135343.2886 | 21222.5298 |  | Forecast Cost at Completion
FAC | 4091.25 | 1476 | 3543.75 | 3260.625 | 7 | 821 | 2755.75 | 1695 | 11026.375 | 100229 | 117509 | 817774.9828 | 174552.6817 | 371784.79 | 1146245.7728
Variance
459152.2272
Note on D7: Rockliff, Tasha: TBC

## UKRI
Project Dashboard- WON 12570-1022 - UKRI
Month | Forecasted Hours | [12 empty] | External Forecast |  |  |  |  | UKRI Cost - Overview
| Lloyd Fletcher | Joel Hirst | Joel Hirst | Wiera Bielajewa | Wiera Bielajewa | Jonathan Horne-Jones | John Charlton | Graduates x2 (TBC) | Christopher Dawson | Year In Industry Students | Kiyana Patel | James Panayis | FC Hours - Total | Travel | External Spend | UKRI Forecast Spend (80% +All expenses) | UKAEA Shortfall (20%) £401,349 Budget | Total Spend to date - UKRI ONLY
Grade | UKAXI | UKAXE | UKAXG | UKAXE | UKAXF | N/A | N/A | UKL3 | UKAXE | N/A | UKAXE | UKAXE
FY24/25 | 874 | 527 | 0 | 0 | 0 | 0 | 570 | 0 | 0 |  | 0 | 0 |  | 642 | 5232 | 0 | 0 | 116616.82 | Grant Contribution Budget
FY25/26 | 1091 | 949 | 0 | 780 | 780 | 7 | 251 | 0 | 472.5 |  | 0 | 0 |  | 5048 | 17738 | 0 | 0 | 211853.97
FY26/27 | 945 | 787.5 | 787.5 | 551.25 | 551.25 | 0 | 0 | 1574 | 472.5 | 2362.5 | 472.5 | 420 | 8924 | 6000 | 20000 | 398812.0518 | 99703.0129 | 43314 | 1605398
FY27/28 | 945 | 0 | 1575 | 0 | 1575 | 0 | 0 | 3150 | 0 | 787.5 | 0 | 0 | 8032.5 | 6000 | 20000 | 422839.7332 | 105709.9333
FY28/29 | 393.75 | 0 | 656.25 | 0 | 656.25 | 0 | 0 | 1312.5 |  | 0 | 0 | 0 | 3018.75 | 6000 | 20000 | 199097.5897 | 49774.3974 |  | Forecast Cost at Completion
FAC | 4248.75 | 2263.5 | 3018.75 | 1331.25 | 3562.5 | 7 | 821 | 6036.5 | 945 | 3150 | 472.5 | 420 | 19975.25 | 23690 | 82970 | 1020749.3746 | 255187.3437 | 371784.79 | 1349220.1646
Variance
FY 26/27
| Fixed Issues Reducing Variance | [14 empty] | Year in Industry | J25 |  | 256177.8354
| 1 | Last year of UKRI FLF is until end of Aug so 5 months, not 3 months - fixing this drastically reduced variance | [13 empty] | UKAXF | J22
| 2 | Intermediate grades costed lower: UKAXF costed at UKM4 rate, fixed to be halfway between for UKAXF and UKAXH | [13 empty] | UKAXH | J23
| 3 | Year in industry students not costed for
FY 26/27
| Updated based on new information | [14 empty] | UKL3 | E16
| 1 | Adel -> H after appeal | [13 empty] | UKM3 | E22
| 2 | Alex's resignation date and Rob's starting date accounted for on UKAEA sheet | [13 empty] | UKM4 | E23
| 3 | Adjusted travel and external spend costs based on FY 25/26 actual expenditure | [13 empty] | UKM5 | E24
| 4 | No external spend other than PhDs on UKAEA code | [13 empty] | UKM6 | E25
| 5 | Promotions for Joel/Wiera corrected based on projected dates
[16 empty] | 26/27 | E | J
[16 empty] | 27/28 | F | K
[16 empty] | 28/29 | G | L
Note on D7: Rockliff, Tasha: TBC