## Rates
Project summary
Approved PJD
Project Lead
Project Manager | Tasha Rockliff
ProgramArea Manager | Insert name
Links to task specifications | Insert link(s) | [7 empty] | =((D7*'Project Overview'!'Project Overview'!42:42D42)+(E7*'Project Overview'!D23)+(F7*'Project Overview'!D24))*1.4
Total person resource hours
Total capital spend
| Cost.cat | FY25/26 | FY26/27 | FY27/28 | FY28/29 | Overhead Rate | 1.4
| UKA1 | 17.32 | 18.0128 | 18.7333 | 19.4826
| UKA2 | 38.85 | 40.404 | 42.0202 | 43.701
| UKL1 | 26.43 | 27.4872 | 28.5867 | 29.7302
| UKL2 | 26.43 | 27.4872 | 28.5867 | 29.7302
| UKL3 | 30.85 | 32.084 | 33.3674 | 34.7021
| UKL4 | 38.75 | 40.3 | 41.912 | 43.5885
| UKL5 | 48.03 | 49.9512 | 51.9492 | 54.0272
| UKL6 | 62.14 | 64.6256 | 67.2106 | 69.899
| UKL7 | 74.05 | 77.012 | 80.0925 | 83.2962
| UKL8 | 104.9 | 109.096 | 113.4598 | 117.9982
| UKM3 | 35.29 | 36.7016 | 38.1697 | 39.6965
| UKM4 | 40.4 | 42.016 | 43.6966 | 45.4445
| UKM5 | 54.01 | 56.1704 | 58.4172 | 60.7539 |  |  | 0
| UKM6 | 67.56 | 70.2624 | 73.0729 | 75.9958
| UKM7 | 88.78 | 92.3312 | 96.0244 | 99.8654
| UKMS | 52.67 | 54.7768 | 56.9679 | 59.2466
| UKS3 | 46.7 | 48.568 | 50.5107 | 52.5311
| UKS4 | 54 | 56.16 | 58.4064 | 60.7427
| UKT1 | 23.14 | 24.0656 | 25.0282 | 26.0294
| RU01 | 11.5 | 11.96 | 12.4384 | 12.9359
| RU02 | 14.75 | 15.34 | 15.9536 | 16.5917
| RU03 | 16.5 | 17.16 | 17.8464 | 18.5603
| RU04 | 19.25 | 20.02 | 20.8208 | 21.6536
| RU05 | 21.5 | 22.36 | 23.2544 | 24.1846
| RU06 | 23.75 | 24.7 | 25.688 | 26.7155
| RU07 | 26.5 | 27.56 | 28.6624 | 29.8089
| RU08 | 29 | 30.16 | 31.3664 | 32.6211
| RU09 | 31.25 | 32.5 | 33.8 | 35.152
| RU10 | 33.75 | 35.1 | 36.504 | 37.9642
| RU11 | 36.5 | 37.96 | 39.4784 | 41.0575
| RU12 | 38.5 | 40.04 | 41.6416 | 43.3073
| RU13 | 41.5 | 43.16 | 44.8864 | 46.6819
| RU14 | 44.25 | 46.02 | 47.8608 | 49.7752
| RU15 | 48 | 49.92 | 51.9168 | 53.9935
| RU16 | 53.25 | 55.38 | 57.5952 | 59.899
| RU17 | 58.5 | 60.84 | 63.2736 | 65.8045
| RU18 | 64.5 | 67.08 | 69.7632 | 72.5537
| RU19 | 70 | 72.8 | 75.712 | 78.7405
| RU20 | 75.85 | 78.884 | 82.0394 | 85.3209
| RU23 | 81.7 | 84.968 | 88.3667 | 91.9014
| RU24 | 87.55 | 91.052 | 94.6941 | 98.4818
| RU25 | 90 | 93.6 | 97.344 | 101.2378
| RU26 | 95 | 98.8 | 102.752 | 106.8621
| RU27 | 100 | 104 | 108.16 | 112.4864
| RU28 | 105 | 109.2 | 113.568 | 118.1107
| RU29 | 110 | 114.4 | 118.976 | 123.735
| RU30 | 115 | 119.6 | 124.384 | 129.3594
| RU31 | 120 | 124.8 | 129.792 | 134.9837
| RU32 | 125 | 130 | 135.2 | 140.608
| UNI2 | 56.7 | 58.968 | 61.3267 | 63.7798
| IND1 | 110 | 114.4 | 118.976 | 123.735
| IND2 | 72 | 74.88 | 77.8752 | 80.9902
| IND3 | 55 | 57.2 | 59.488 | 61.8675
| IND4 | 65 | 67.6 | 70.304 | 73.1162
| IND5 | 82 | 85.28 | 88.6912 | 92.2388
| IND6 | 69 | 71.76 | 74.6304 | 77.6156
| IND7 | 38 | 39.52 | 41.1008 | 42.7448
| IND8 | 60 | 62.4 | 64.896 | 67.4918
| IND9 | 90 | 93.6 | 97.344 | 101.2378
| IND10 | 120 | 124.8 | 129.792 | 134.9837
| IND11 | 100 | 104 | 108.16 | 112.4864
| IND12 | 50 | 52 | 54.08 | 56.2432
| IND13 | 65 | 67.6 | 70.304 | 73.1162
| IND14 | 70 | 72.8 | 75.712 | 78.7405
| IND15 | 55 | 57.2 | 59.488 | 61.8675
| IND16 | 105 | 109.2 | 113.568 | 118.1107
| IND17 | 95 | 98.8 | 102.752 | 106.8621
| IND18 | 46 | 47.84 | 49.7536 | 51.7437
| IND19 | 115 | 119.6 | 124.384 | 129.3594
| IND20 | 170 | 176.8 | 183.872 | 191.2269
| IND21 | 135 | 140.4 | 146.016 | 151.8566
| IND22 | 129 | 134.16 | 139.5264 | 145.1075
| IND23 | 87 | 90.48 | 94.0992 | 97.8632
| IND24 | 160 | 166.4 | 173.056 | 179.9782
| IND25 | 77 | 80.08 | 83.2832 | 86.6145
| IND26 | 125 | 130 | 135.2 | 140.608

## June 26 - UKAEA (hidden)
Project Dashboard- WON 13875-1000
Month | Forecasted Hours | [18 empty] | Forcasted Spend |  | Annual Budget |  | Actual Spend | Total Project Cost - Overview
| Lloyd Fletcher | Joel Hirst | Joel Hirst | Wiera Bielajewa | Christopher Dawson | Adel Tayeb | Nell Morris | Rory Spencer | Megan Sampson | Alexander Marsh | John Charlton | FC - Total | Rushavya Naidu | Lucas Pigott | Student 1 | Student 2 | Total PhD Cost | Travel | External Spend | UKAEA Resource Spend ONLY | UKAEA Forecast Spend | UKAEA Annual Budget | Variance from Budget | Actual Spend to date
Grade | UKAXI | UKAXE | UKAXG | UKAXE | UKAXE | UKM5 | UKL3 | UKM5 | UKM4 | UKM4 | UKM4 |  | PhD Student
FTE | 0.3 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 | 0.2 | 1 | 0
FY24/25 | 24 | 0 | 0 | 0 | 0 | 948 | 0 | 0 | 0 | 809 | 0 | 1781 |  |  |  |  | 0 | 627 | 215 | 0 | 0 | 0 |  | 95819.57 | Project Budget
FY25/26 | 1091 | 949 | 0 | 780 | 0 | 957 | 10 | 58 | 358 | 1393 | 251 | 5847 | 7778 | 8072 | 0 | 0 | 15850 | 4370 | 27014 | 0 | 0 | 300000 |  | 268870.79
FY26/27 | 472.5 | 0 | 0 | 0 | 0 | 1417.5 | 0 | 0 | 315 | 1575 | 0 | 3780 | 15685 | 16378 | 7924.5 | 7924.5 | 47912 | 18000 | 47911 | 112609.224 | 226432.224 | 381973.39 | 155541.166 | 30849.55 | 1255259.7
FY27/28 | 472.5 | 0 | 0 | 0 | 0 | 1417.5 | 0 | 0 | 315 | 1575 | 0 | 3780 | 15945.25 | 16854 | 16030.5 | 16030.5 | 64860.25 | 18000 | 64860 | 117113.593 | 264833.843 | 381973.39 | 117139.547
FY28/29 | 236.25 | 0 | 0 | 0 | 0 | 708.75 | 0 | 0 | 157.5 | 787.5 | 0 | 1890 | 8105.125 | 8674 | 16399.5 | 16399.5 | 49578.125 | 9000 | 33106 | 60899.0683 | 152583.1933 | 95493.35 | -57089.8433 |  | Forecast Cost at Completion
FAC | 2296.25 | 949 | 0 | 780 | 0 | 5448.75 | 10 | 58 | 1145.5 | 6139.5 | 251 | 17078 | 47513.375 | 49978 | 40354.5 | 40354.5 | 178200.375 | 49997 | 173106 | 290621.8853 | 643849.2603 | 1159440.13 |  | 395539.91 | 1008539.6203
Note on AD14: Rockliff, Tasha: Amend with each update

## UKAEA
Project Dashboard- WON 13875-1000
Month | Forecasted Hours | [19 empty] | Forcasted Spend |  | Annual Budget |  | Actual Spend | Total Project Cost - Overview
| Lloyd Fletcher | Joel Hirst | Joel Hirst | Wiera Bielajewa | Christopher Dawson | Adel Tayeb | Rob Hamill | Nell Morris | Rory Spencer | Megan Sampson | Alexander Marsh | John Charlton | FC - Total | Rushavya Naidu | Lucas Pigott | Student 1 | Student 2 | Total PhD Cost | Travel | External Spend | UKAEA Resource Spend ONLY | UKAEA Forecast Spend | UKAEA Annual Budget | Variance from Budget | Actual Spend to date
Grade | UKAXI | UKAXE | UKAXG | UKAXE | UKAXE | UKM5 | UKAXF | UKL3 | UKM5 | UKM4 | UKM4 | UKM4 |  | PhD Student
FTE | 0.3 | 0 | 0 | 0 | 0 | 0.9 | 1 | 0 | 0 | 0.2 | 1 | 0
FY24/25 | 24 | 0 | 0 | 0 | 0 | 948 | 0 | 0 | 0 | 0 | 809 | 0 | 1781 |  |  |  |  | 0 | 627 | 215 | 0 | 0 | 0 |  | 95819.57 | Project Budget
FY25/26 | 1091 | 949 | 0 | 780 | 0 | 957 | 0 | 10 | 58 | 358 | 1393 | 251 | 5847 | 7778 | 8072 | 0 | 0 | 15850 | 4370 | 27014 | 0 | 0 | 300000 |  | 268870.79
FY26/27 | 472.5 | 0 | 0 | 0 | 0 | 1417.5 |  | 0 | 0 | 315 | 1575 | 0 | 3780 | 15685 | 16378 | 7924.5 | 7924.5 | 47912 | 18000 | 47911 | 112609.224 | 226432.224 | 381973.39 | 155541.166 | 30849.55 | 1255259.7
FY27/28 | 472.5 | 0 | 0 | 0 | 0 | 1417.5 |  | 0 | 0 | 315 | 1575 | 0 | 3780 | 15945.25 | 16854 | 16030.5 | 16030.5 | 64860.25 | 18000 | 64860 | 117113.593 | 264833.843 | 381973.39 | 117139.547
FY28/29 | 236.25 | 0 | 0 | 0 | 0 | 708.75 |  | 0 | 0 | 157.5 | 787.5 | 0 | 1890 | 8105.125 | 8674 | 16399.5 | 16399.5 | 49578.125 | 9000 | 33106 | 60899.0683 | 152583.1933 | 95493.35 | -57089.8433 |  | Forecast Cost at Completion
FAC | 2296.25 | 949 | 0 | 780 | 0 | 5448.75 |  | 10 | 58 | 1145.5 | 6139.5 | 251 | 17078 | 47513.375 | 49978 | 40354.5 | 40354.5 | 178200.375 | 49997 | 173106 | 290621.8853 | 643849.2603 | 1159440.13 |  | 395539.91 | 1008539.6203
[7 empty] | Starts Dec 2026 |  |  |  | Resigns end July 2026
Note on AE14: Rockliff, Tasha: Amend with each update

## June 26 - UKRI (hidden)
Project Dashboard- WON 12570-1022 - UKRI
Month | Forecasted Hours | [8 empty] | External Forecast |  |  |  |  | UKRI Cost - Overview
| Lloyd Fletcher | Joel Hirst | Joel Hirst | Wiera Bielajewa | Jonathan Horne-Jones | John Charlton | Graduate (TBC) | Christopher Dawson | FC Hours - Total | Travel | External Spend | UKRI Forecast Spend (80% +All expenses) | UKAEA Shortfall (20%) £401,349 Budget | Total Spend to date - UKRI ONLY
Grade | UKAXI | UKAXE | UKAXG | UKAXE |  |  | UKL3 | UKAXE
FY24/25 | 874 | 527 | 0 | 0 | 0 | 570 | 0 | 0 |  | 642 | 5232 | 0 | 0 | 116616.82 | Grant Contribution Budget
FY25/26 | 1091 | 949 | 0 | 780 | 7 | 251 | 0 | 1575 |  | 5048 | 17738 | 0 | 0 | 211853.97
FY26/27 | 945 | 0 | 1575 | 1102.5 | 0 | 0 | 787 | 120 | 4529.5 | 32492 | 32492 | 324242.7379 | 71705.037 | 43314 | 1605398
FY27/28 | 945 | 0 | 1575 | 1102.5 | 0 | 0 | 1575 | 0 | 5197.5 | 32492 | 32492 | 358188.9563 | 81625.1148
FY28/29 | 236.25 | 0 | 393.75 | 275.625 | 0 | 0 | 393.75 | 0 | 1299.375 | 29555 | 29555 | 135343.2886 | 21222.5298 |  | Forecast Cost at Completion
FAC | 4091.25 | 1476 | 3543.75 | 3260.625 | 7 | 821 | 2755.75 | 1695 | 11026.375 | 100229 | 117509 | 817774.9828 | 174552.6817 | 371784.79 | 1146245.7728
Variance
459152.2272
Note on D7: Rockliff, Tasha: TBC

## UKRI
Project Dashboard- WON 12570-1022 - UKRI
Month | Forecasted Hours | [9 empty] | External Forecast |  |  |  |  | UKRI Cost - Overview
| Lloyd Fletcher | Joel Hirst | Joel Hirst | Wiera Bielajewa | Wiera Bielajewa | Jonathan Horne-Jones | John Charlton | Graduates x2 (TBC) | Christopher Dawson | FC Hours - Total | Travel | External Spend | UKRI Forecast Spend (80% +All expenses) | UKAEA Shortfall (20%) £401,349 Budget | Total Spend to date - UKRI ONLY
Grade | UKAXI | UKAXE | UKAXG | UKAXF | UKAXE |  |  | UKL3 | UKAXE
FY24/25 | 874 | 527 | 0 | 0 | 0 | 0 | 570 | 0 | 0 |  | 642 | 5232 | 0 | 0 | 116616.82 | Grant Contribution Budget
FY25/26 | 1091 | 949 | 0 | 780 | 780 | 7 | 251 | 0 | 1575 |  | 5048 | 17738 | 0 | 0 | 211853.97
FY26/27 | 945 | 0 | 1575 | 1102.5 | 1102.5 | 0 | 0 | 1574 | 472.5 | 6771.5 | 32492 | 32492 | 369110.7757 | 101247.692 | 43314 | 1605398
FY27/28 | 945 | 0 | 1575 | 1575 | 1575 | 0 | 0 | 3150 | 0 | 8820 | 32492 | 32492 | 440173.2412 | 133675.2144
FY28/29 | 236.25 | 0 | 393.75 | 393.75 | 393.75 | 0 | 0 | 787.5 | 0 | 2205 | 29555 | 29555 | 156659.2027 | 34755.5557 |  | Forecast Cost at Completion
FAC | 4091.25 | 1476 | 3543.75 | 3851.25 | 3851.25 | 7 | 821 | 5511.5 | 2047.5 | 17796.5 | 100229 | 117509 | 965943.2196 | 269678.4621 | 371784.79 | 1294414.0096
Variance
310983.9904
Note on D7: Rockliff, Tasha: TBC